## Activities
Stage | Activity | Comments | System | Responsible | Status (Completed/In progress) | Estimated time | Required for BYOD, EDL or Both | Guidance
Confirm minimum version
| Dynamics 365 Finance version | Your environments should be on supported version: 10.0.36 (PU60) cumulative update 7.0.7036.133 or later. 10.0.37 (PU61) cumulative update 7.0.7068.109 or later. 10.0.38 (PU62) cumulative update 7.0.7120.59 or later | Dynamics 365/LCS | Dynamics Application Admin |  |  | Both | Choose finance and operations data in Azure Synapse Link for Dataverse - Power Apps ¦ Microsoft Learn
| Dynamics 365/Dataverse version | Microsoft Dynamics 365 minimum version requirement to use this feature is 9.2.22082. Dataverse: You must have the Dataverse system administrator security role. | Dynamics 365 | Dynamics Application Admin |  |  | Both
Enable Dynamics 365 tables
| Identify all tables and entities you want to export in the PoC |  | Dynamics 365 | Project team |  |  | Both
| Identify known gaps and exclude those tables from PoC | Please read the link to know the gaps | Dynamics 365 | Project team |  |  | Both | Choose finance and operations data in Azure Synapse Link for Dataverse - Power Apps ¦ Microsoft Learn
| Sql row version change tracking key | Enable a configuration key in the F&O instance you want to export data from. To do this, you enable the maintenance mode for the environment in LCS. Then, go to System administration > Setup > License configuration. Look for the Sql row version change tracking key and enable it | Dynamics 365/LCS | Dynamics Application Admin |  |  | Both | Choose finance and operations data in Azure Synapse Link for Dataverse - Power Apps ¦ Microsoft Learn
| Enable Sql row version change tracking on any custom tables | This so any custom tables and entities can also export data | Dynamics 365/LCS | Developer |  |  | Both | Row version change tracking for tables and data entities - Finance & Operations ¦ Dynamics 365 ¦ Microsoft Learn
| Enable Sql row version change tracking on any custom entities | This so any custom entities can also export data | Dynamics 365/LCS | Developer |  |  | BYOD | Row version change tracking for tables and data entities - Finance & Operations ¦ Dynamics 365 ¦ Microsoft Learn
Decisions
| Will you maintain the legacy EDL columns? | If you are migrating from EDL to Synapse Link, there are a few changes between the audit columns. FastTrack has created a template pipeline that can be used to add the EDL audit columns, however this will require maintenance. |  |  |  |  | EDL | Dynamics-365-FastTrack-Implementation-Assets/Analytics/DataverseLink/Dynamics365_ExportToDataLake_To_Synapse_Link_TransitionGuide_Deepdive.pptx at master · microsoft/Dynamics-365-FastTrack-Implementation-Assets (github.com) Dynamics-365-FastTrack-Implementation-Assets/Analytics/DataverseLink/DataIntegration at master · microsoft/Dynamics-365-FastTrack-Implementation-Assets (github.com)
| Will you remove the mserp_ prefix from exported entities? | If you are migrating from BYOD to Synapse Link, there are a few changes between the BYOD database schema and the Synapse database schema for OOB entities. FastTrack has created a template pipeline that can be used to remove the mserp_ prefix, however this will require maintenance. |  |  |  |  | BYOD | Dynamics-365-FastTrack-Implementation-Assets/Analytics/DataverseLink/DataIntegration at master · microsoft/Dynamics-365-FastTrack-Implementation-Assets (github.com)
| Will you export incremental CSV files? | This is one of the three options to access D365 data |  |  |  |  | Both
| Will you export parquet / delta files? | This is one of the three options to access D365 data |  |  |  |  | Both
| Will you use Microsoft OneLake? | This is one of the three options to access D365 data |  |  |  |  | Both
| What end state architecture will you use? | Depending on what end state you want, you may choose one of the three options - Synapse link delta lake path or Synapse link csv path or Fabric link path. You can also deploy more than 1 option. You can follow those steps below. |  |  |  |  | Both
| Will you leverage complex entities and use the powershell script (EntityUtil) or build relationships externally? | Synapse link exports Dynamics 365 tables and entities. Not all entities are exported. If you need to export all, there is a powershell script you need to run. Or can create views manually. |  |  |  |  | BYOD | DataverseLink/DataIntegration/EntityUtil
Create Azure resources and Setup Synapse link
| Create/Confirm an Azure storage account (data lake) | You must have an Azure Data Lake Storage Gen2 account and Owner and Storage Blob Data Contributor role access. Your storage account must enable Hierarchical namespace and public network access for both initial setup and delta sync. Allow storage account key access is required only for the initial setup. | Azure portal | Azure Subscription Owner/ Contributor
| Create/Confirm Azure Synapse Workspace | You must have a Synapse workspace and Owner role in access control(IAM) and the Synapse Administrator role access within the Synapse Studio. The Synapse workspace must be in the same region as your Azure Data Lake Storage Gen2 account. The storage account must be added as a linked service within the Synapse Studio. | Azure portal | Azure Subscription Owner/ Contributor |  |  |  | Quickstart: Get started - create a Synapse workspace - Azure Synapse Analytics ¦ Microsoft Learn
| Create a Spark pool | Spark pool converts exported Dynamics 396 data from csv format to delta lake format and stores in the Azure Data Lake Storage Gen2 account. Create a Spark Pool in the connected Azure Synapse workspace with Apache Spark Version 3.3 using the recommended Spark Pool configuration. This configuration can be considered a bootstrap step for average use cases. Node size: small (4 vCores / 32 GB) Autoscale: Enabled Number of nodes: 5 to 10 Automatic pausing: Enabled Number of minutes idle: 5 Apache Spark: 3.3 | Azure Synapse/Azure Portal | Azure Subscription Owner/ Contributor |  |  |  | Quickstart: Create a serverless Apache Spark pool using the Azure portal - Azure Synapse Analytics ¦ Microsoft Learn
| Create Synapse Link - spark pool option | Synapse link will transport your Dynamics 365 data via Dataverse to an instance of a storage account (data lake) or Azure Synapse workspace hosted in your subscription. You also get a ready to use lake database in Synapse workspace. The files have been converted to delta lake format by the spark pool. | Power Maker portal | Dynamics App Admin Will require access to Azure |  |  |  | Export Microsoft Dataverse data in Delta Lake format - Power Apps ¦ Microsoft Learn
| Create Synapse Link - timestamped folders option | You can also setup Synapse link to create timestamped folders with incremental changes as csv files. If you only need this option, you need Storage account and don’t need Azure Synapse Workspace and Spark pool. | [5 empty] | Query and analyze the incremental updates - Power Apps ¦ Microsoft Learn
Buy capacity and Setup Fabric Link
| Enable Fabric Trial | Microsoft Fabric is provided free of charge when you sign up for the Fabric trial. Your use of the Microsoft Fabric trial includes access to the Fabric product experiences and the resources to create and host Fabric items. The Fabric trial lasts for 60 days, but can be extended by Microsoft, at our discretion. | Microsoft Fabric | Dynamics App Admin/ Power BI Administrator |  |  |  | Fabric trial - Microsoft Fabric
| Or Buy a Fabric Capacity |  | Azure | Azure Subscription Owner/ Contributor |  |  |  | Buy a Microsoft Fabric subscription
| Create Fabric Link | Link to Fabric feature enables direct connectivity between your data in Dataverse with Microsoft Fabric without the need to bring your own storage and Synapse workspaces. Link to Fabric leverages storage built into Dataverse and removes the need to provision and manage your own storage. | Power platform maker portal | Dynamics Application Admin |  |  |  | Link your Dataverse environment to Microsoft Fabric
Add tables and entities
| Add Dynamics 365 Finance Tables/Entities to Synapse link |  | Power platform maker portal | Dynamics 365 admin |  |  |  | Choose finance and operations data in Azure Synapse Link for Dataverse - Power Apps ¦ Microsoft Learn
| Or Add Dynamics 365 Finance tables and entities to Fabric Link | In Fabric link, all Dataverse tables are selected by default. You can add D365 Finance tables/entities | Power platform maker portal | Dynamics 365 admin |  |  |  | Link your Dataverse environment to Microsoft Fabric and unlock deep insights - Power Apps ¦ Microsoft Learn
Data integration to third party DW
| Create pipeline to move data to 3rd-party systems (if required) | If you need to integrate to Azure SQL or 3rd party systems like, Snowflake or Google cloud or AWS, appropriate work is required. |  | Developer
Testing
| Check the Synapse "lake database" is created and accessible | You should be able to query the tables using tsql or spark | Azure Synapse/Power Maker portal | Synapse admin/User |  |  |  | A post on creating lakehouse - https://community.dynamics.com/blogs/post/?postid=43e3da30-a2c0-ee11-92bd-6045bdaf8c56
| Or Check the Fabric "lakehouse" is created and accessible | You should be able to query the tables using tsql or spark | Fabric workspace | Fabric workspace user
| Test the initial data is flowing to data lake and Azure Synapse/Fabric | Check the Power Maker portal > Synapse link profile > Tables if the tables Sync status is 'Active'. If not, see if they show in 'Error'. | Power Maker portal | Testing team
| Test incremental changes are flowing to data lake and Azure Synapse/Fabric | Do inserts, updates and deletes in D365 and these should be reflected in data lake folders and in Synapse lake database or Fabric lakehouse | Azure Synapse/Fabric | Testing team |  |  |  | Another method to get changes - https://community.dynamics.com/blogs/post/?postid=37e11b6c-a4c0-ee11-92bd-6045bdaf8c56
| Test any integrations | If you have third party tools connecting to data lake or Azure Synapse/Fabric, you need to validate they work. | Azure Synapse/Fabric | Testing team
D365 Synapse Link / Fabric Link Migration Activities